## Gantt
Carbon Removal Verification Registry (CRVR) — Gantt Chart
ITCS514 Software Project Management · Group 1 · Charter v2.00 · 50 activities across 11 phases · critical path 65 working days · start Mon 28 Sep 2026 · Weeks 13–14 buffer · satellite monitoring & inter-registry hook deferred (not scheduled)
ID | Activity | WBS ref | Owner | Type | Start Date | Due Date | Dur (d) | Predecessors | Float (d) | Critical | W0 |  |  |  |  | W1 |  |  |  |  | W2 |  |  |  |  | W3 |  |  |  |  | W4 |  |  |  |  | W5 |  |  |  |  | W6 |  |  |  |  | W7 |  |  |  |  | W8 |  |  |  |  | W9 |  |  |  |  | W10 |  |  |  |  | W11 |  |  |  |  | W12 |  |  |  |  | W13 |  |  |  |  | W14
[11 empty] | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
| Ongoing — management & agile ceremonies | Weeks 0–14 |  | Summary | 2026-09-28 | 2027-01-08 | 75
PM1 | Project management, reporting & change control | 1.1, 1.3 | Project Manager | Hammock | 2026-09-28 | 2027-01-08 | 75 | — | 0
1.1.1 | Project charter & stakeholder register |  | Project Manager | Work package |  |  | 5
1.3.1 | Weekly reporting & change control |  | Project Manager | Work package |  |  | 8
CER | Agile ceremonies — planning, stand-ups, review, retro | 1.5 | Shared — whole team | Level of effort | 2026-10-12 | 2026-12-18 | 50 | — | 15 | bar: W2 M to W11 F
1.5.1 | Sprint planning & backlog refinement |  | Project Manager | Work package |  |  | 4
1.5.2 | Daily stand-ups |  | Shared — whole team | Work package |  |  | 3
1.5.3 | Sprint review & demo |  | Shared — whole team | Work package |  |  | 3
1.5.4 | Sprint retrospective |  | Project Manager | Work package |  |  | 2
RC | Change-request analysis & impact assessment | 2.4.1 | Business Analyst | Level of effort | 2026-10-26 | 2026-12-25 | 45 | — | 10 | bar: W4 M to W12 F
2.4.1 | Change-request analysis & impact assessment |  | Business Analyst | Work package |  |  | 5
BC | Risk register & budget proposal | 1.2.2, 1.2.3 | Project Manager | Level of effort | 2026-10-12 | 2026-11-06 | 20 | — | 45 | bar: W2 M to W5 F
1.2.2 | Risk register |  | Project Manager | Work package |  |  | 3
1.2.3 | Cost estimate & budget proposal |  | Project Manager | Work package |  |  | 4
SR1 | ◆ Sprint 1 review & demo | 1.5.3 | Shared — whole team | Milestone | 2026-10-23 | 2026-10-23 | 0 | — | 55 | bar: W4 M
SR2 | ◆ Sprint 2 review & demo | 1.5.3 | Shared — whole team | Milestone | 2026-11-06 | 2026-11-06 | 0 | — | 45 | bar: W6 M
SR3 | ◆ Sprint 3 review & demo | 1.5.3 | Shared — whole team | Milestone | 2026-11-20 | 2026-11-20 | 0 | — | 35 | bar: W8 M
| Initiation & Mobilisation | Week 0 |  | Summary | 2026-09-28 | 2026-10-02 | 5 | bar: W0 M to W0 F
A | Mobilisation & environment provisioning | 11.1.1 | Infrastructure / DevOps | Task | 2026-09-28 | 2026-10-02 | 5 | — | 0 | YES | bar: W0 M to W0 F
11.1.1 | Dev / test provisioning |  | Infrastructure / DevOps | Work package |  |  | 3
| Planning, Requirements & Technical Validation | Weeks 0–2 |  | Summary | 2026-09-28 | 2026-10-16 | 15 | bar: W0 M to W2 F
B | Scope, WBS & schedule baseline | 1.2.1 | Project Manager | Task | 2026-10-05 | 2026-10-09 | 5 | A | 0 | YES | bar: W1 M to W1 F
1.2.1 | WBS & schedule baseline |  | Project Manager | Work package |  |  | 4
RQ | Requirements elicitation & as-is analysis | 2.1 | Business Analyst | Task | 2026-09-28 | 2026-10-06 | 7 | — | 0 | YES | bar: W0 M to W1 T
2.1.1 | Stakeholder requirements workshops |  | Business Analyst | Work package |  |  | 4
2.1.2 | As-is verification process & gap analysis |  | Business Analyst | Work package |  |  | 3
RS | Requirements specification & user stories | 2.2 | Business Analyst | Task | 2026-10-07 | 2026-10-16 | 8 | RQ | 0 | YES | bar: W1 W to W2 F
2.2.1 | Functional requirements specification (FR-01…FR-11) |  | Business Analyst | Work package |  |  | 4
2.2.2 | Non-functional, security & integration requirements |  | Business Analyst | Work package |  |  | 2
2.2.3 | User stories & acceptance criteria |  | Business Analyst | Work package |  |  | 2
C | Spike: satellite data provider | 3.1.1 | Infrastructure / DevOps | Task | 2026-10-05 | 2026-10-09 | 5 | A | 0 | YES | bar: W1 M to W1 F
3.1.1 | Satellite data provider spike |  | Infrastructure / DevOps | Work package |  |  | 5
D | Spike: geospatial / PostGIS | 3.1.2 | Full-stack Dev ×4 | Task | 2026-10-05 | 2026-10-09 | 5 | A | 0 | YES | bar: W1 M to W1 F
3.1.2 | Geospatial / PostGIS spike |  | Full-stack Dev ×4 | Work package |  |  | 5
| Sprint 1 — Design & Scope Lock | Weeks 2–3 |  | Summary | 2026-10-12 | 2026-10-23 | 10 | bar: W2 M to W3 F
E | UX: developer portal | 3.3.1 | Designer ×2 | Task | 2026-10-12 | 2026-10-16 | 5 | B | 1 | bar: W2 M to W2 F
3.3.1 | Developer portal UX (responsive, phone width) |  | Designer ×2 | Work package |  |  | 5
F | UX: buyer & verifier portal | 3.3.2 | Designer ×2 | Task | 2026-10-19 | 2026-10-23 | 5 | E | 10 | bar: W3 M to W3 F
3.3.2 | Buyer & verifier portal UX |  | Designer ×2 | Work package |  |  | 5
G | System architecture & data model | 3.2.1, 3.2.2 | Infrastructure / DevOps | Task | 2026-10-12 | 2026-10-16 | 5 | B, C, D | 0 | YES | bar: W2 M to W2 F
3.2.1 | Architecture & integration design |  | Infrastructure / DevOps | Work package |  |  | 5
3.2.2 | Data model & access-control matrix |  | Full-stack Dev ×4 | Work package |  |  | 4
H | Ledger + WORM architecture | 3.2.3 | Security Engineer ×2 | Task | 2026-10-19 | 2026-10-21 | 3 | G | 0 | YES | bar: W3 M to W3 W
3.2.3 | Ledger + WORM storage design |  | Security Engineer ×2 | Work package |  |  | 3
HF | Hi-fi hands-on review — Sponsor, CEO, board member, champion customer | 3.3.3 | Designer ×2 | Task | 2026-10-19 | 2026-10-20 | 2 | E | 1 | bar: W3 M to W3 T
3.3.3 | Hi-fi hands-on review — board member & champion customer |  | Designer ×2 | Work package |  |  | 2
RV | Requirements traceability & baseline sign-off | 2.3 | Business Analyst | Task | 2026-10-19 | 2026-10-21 | 3 | RS | 0 | YES | bar: W3 M to W3 W
2.3.1 | Requirements traceability matrix |  | Business Analyst | Work package |  |  | 2
2.3.2 | Requirements baseline & sign-off |  | Business Analyst | Work package |  |  | 1
QP | Test plan & test case design | 10.1.1 | QA Engineer | Task | 2026-10-19 | 2026-10-23 | 5 | RS | 0 | YES | bar: W3 M to W3 F
10.1.1 | Test plan, cases & test data |  | QA Engineer | Work package |  |  | 5
I | Design review & scope lock | 3.3.4 | Project Manager | Task | 2026-10-22 | 2026-10-23 | 2 | E, H, RV, HF | 0 | YES | bar: W3 T to W3 F
3.3.4 | Design review & scope lock |  | Project Manager | Work package |  |  | 2
SL | ◆ Scope locked | 3.3.4 | Project Manager | Milestone | 2026-10-23 | 2026-10-23 | 0 | I | 0 | YES | bar: W4 M
| Sprint 2 — Core Build | Weeks 4–5 |  | Summary | 2026-10-26 | 2026-11-06 | 10 | bar: W4 M to W5 F
J | Authentication & RBAC | 9.1.1, 9.1.2 | Security Engineer ×2 | Task | 2026-10-26 | 2026-11-06 | 10 | SL | 0 | YES | bar: W4 M to W5 F
9.1.1 | Authentication (Keycloak/Auth0) |  | Security Engineer ×2 | Work package |  |  | 4
9.1.2 | Role-based access control |  | Security Engineer ×2 | Work package |  |  | 5
K | Registration & evidence module | 4.0 | Designer ×2 | Task | 2026-10-26 | 2026-11-06 | 10 | SL | 0 | YES | bar: W4 M to W5 F
4.1.1 | Submission form & validation rules |  | Designer ×2 | Work package |  |  | 5
4.1.2 | Additionality reasoning capture |  | Full-stack Dev ×4 | Work package |  |  | 4
4.2.1 | Evidence upload service |  | Full-stack Dev ×4 | Work package |  |  | 4
4.2.2 | WORM storage integration |  | Infrastructure / DevOps | Work package |  |  | 4
4.3.1 | Status tracking & dashboard |  | Designer ×2 | Work package |  |  | 4
L | Geospatial boundary & map | 5.1, 5.2 | Full-stack Dev ×4 | Task | 2026-10-26 | 2026-11-06 | 10 | SL, D | 0 | YES | bar: W4 M to W5 F
5.1.1 | Data model & PostGIS setup |  | Full-stack Dev ×4 | Work package |  |  | 4
5.1.2 | Boundary registration service |  | Full-stack Dev ×4 | Work package |  |  | 5
5.1.3 | GPS / geospatial file ingestion |  | Full-stack Dev ×4 | Work package |  |  | 4
5.2.1 | Responsive map-drawing interface (phone width) |  | Full-stack Dev ×4 | Work package |  |  | 5
QT2 | Sprint 2 testing — module & acceptance | 10.2.1, 10.3 | QA Engineer | Task | 2026-10-26 | 2026-11-06 | 10 | SL, QP | 0 | YES | bar: W4 M to W5 F
10.2.1 | Sprint 2 in-sprint module testing |  | QA Engineer | Work package |  |  | 5
10.3.1 | Acceptance test scenarios from user stories |  | Business Analyst | Work package |  |  | 3
10.3.2 | Sprint 2 acceptance testing (QA + BA) |  | QA Engineer | Work package |  |  | 4
| Sprint 3 — Integration Build | Weeks 6–7 |  | Summary | 2026-11-09 | 2026-11-20 | 10 | bar: W6 M to W7 F
QT3 | Sprint 3 testing — module & acceptance | 10.2.2, 10.3 | QA Engineer | Task | 2026-11-09 | 2026-11-20 | 10 | QT2 | 0 | YES | bar: W6 M to W7 F
10.2.2 | Sprint 3 in-sprint module testing |  | QA Engineer | Work package |  |  | 5
10.3.3 | Sprint 3 acceptance testing (QA + BA) |  | QA Engineer | Work package |  |  | 4
10.3.4 | Acceptance sign-off & defect capture |  | Business Analyst | Work package |  |  | 3
M | Overlap detection engine & gate | 5.3 | Full-stack Dev ×4 | Task | 2026-11-09 | 2026-11-20 | 10 | L | 0 | YES | bar: W6 M to W7 F
5.3.1 | Overlap engine & tolerance rules |  | Full-stack Dev ×4 | Work package |  |  | 5
5.3.2 | Flagging & pre-issuance gate |  | Full-stack Dev ×4 | Work package |  |  | 4
O | Verification workflow | 7.1, 7.2 | Full-stack Dev ×4 | Task | 2026-11-09 | 2026-11-20 | 10 | J, K | 0 | YES | bar: W6 M to W7 F
7.1.1 | Assignment & evidence access |  | Full-stack Dev ×4 | Work package |  |  | 4
7.1.2 | Verifier workspace UI |  | Designer ×2 | Work package |  |  | 4
7.2.1 | Verification report submission |  | Designer ×2 | Work package |  |  | 4
7.2.2 | Registry review & approval |  | Full-stack Dev ×4 | Work package |  |  | 5
P | Ledger, audit & logging build | 9.1.3, 9.2, 9.3 | Security Engineer ×2 | Task | 2026-11-09 | 2026-11-18 | 8 | J | 2 | bar: W6 M to W7 W
9.1.3 | Separation of duties |  | Security Engineer ×2 | Work package |  |  | 4
9.2.1 | Cryptographic database ledger |  | Security Engineer ×2 | Work package |  |  | 5
9.2.2 | Critical action recording |  | Full-stack Dev ×4 | Work package |  |  | 4
9.3.1 | Action logging & retention |  | Security Engineer ×2 | Work package |  |  | 4
Q | Buyer portal & audit trail | 8.0 | Full-stack Dev ×4 | Task | 2026-11-09 | 2026-11-20 | 10 | K, F | 0 | YES | bar: W6 M to W7 F
8.1.1 | Buyer auth & project access |  | Full-stack Dev ×4 | Work package |  |  | 4
8.1.2 | Status & evidence view |  | Designer ×2 | Work package |  |  | 4
8.2.1 | Buyer-facing audit trail |  | Full-stack Dev ×4 | Work package |  |  | 5
8.2.2 | Credit history & monitoring placeholder |  | Designer ×2 | Work package |  |  | 4
8.3.1 | Privacy filtering & redaction |  | Security Engineer ×2 | Work package |  |  | 4
RD | Mock & test data for E2E and UAT | 11.2.1, 11.2.2 | QA Engineer | Task | 2026-11-09 | 2026-11-13 | 5 | K, L | 5 | bar: W6 M to W6 F
11.2.1 | Pilot selection & evidence gathering |  | Project Manager | Work package |  |  | 2
11.2.2 | Mock & test data set for E2E and UAT |  | Business Analyst | Work package |  |  | 2
| Testing & Remediation | Weeks 7–9 |  | Summary | 2026-11-19 | 2026-12-04 | 12 | bar: W7 T to W9 F
U | End-to-end & usability testing | 10.2.3, 10.2.5 | QA Engineer | Task | 2026-11-23 | 2026-11-27 | 5 | M, O, P, Q, RD, QT3 | 0 | YES | bar: W8 M to W8 F
10.2.3 | End-to-end testing |  | QA Engineer | Work package |  |  | 5
10.2.5 | Usability testing |  | Designer ×2 | Work package |  |  | 3
V | Security testing | 10.2.4 | Security Engineer ×2 | Task | 2026-11-19 | 2026-11-24 | 4 | P | 3 | bar: W7 T to W8 T
10.2.4 | Security testing |  | Security Engineer ×2 | Work package |  |  | 4
PZ | Traceable verification history | 7.3.1 | Full-stack Dev ×4 | Task | 2026-11-23 | 2026-11-26 | 4 | O, P | 1 | bar: W8 M to W8 T
7.3.1 | Traceable verification history |  | Full-stack Dev ×4 | Work package |  |  | 4
W | Defect triage & remediation | 10.4.1 | Shared — whole team | Task | 2026-11-30 | 2026-12-04 | 5 | U, V, QT3, PZ | 0 | YES | bar: W9 M to W9 F
10.4.1 | Triage & remediation verification |  | QA Engineer | Work package |  |  | 5
| Pilot Deployment | Weeks 8–10 |  | Summary | 2026-11-23 | 2026-12-10 | 14 | bar: W8 M to W10 T
X | Production provisioning | 11.1.2 | Infrastructure / DevOps | Task | 2026-11-23 | 2026-11-25 | 3 | M, O, Q | 5 | bar: W8 M to W8 W
11.1.2 | Production provisioning |  | Infrastructure / DevOps | Work package |  |  | 2
XS | Security hardening | 11.1.3 | Security Engineer ×2 | Task | 2026-11-26 | 2026-11-27 | 2 | X | 5 | bar: W8 T to W8 F
11.1.3 | Security hardening |  | Security Engineer ×2 | Work package |  |  | 3
Y | Production deployment & verification | 11.3.1 | Infrastructure / DevOps | Task | 2026-12-07 | 2026-12-10 | 4 | W, XS | 0 | YES | bar: W10 M to W10 T
11.3.1 | Production deployment |  | Infrastructure / DevOps | Work package |  |  | 4
| Board Demonstration | Weeks 10–11 |  | Summary | 2026-12-11 | 2026-12-16 | 4 | bar: W10 F to W11 W
RP | Pilot data load into production (Maker-Checker) | 11.2.3 | Business Analyst | Task | 2026-12-11 | 2026-12-14 | 2 | Y | 2 | bar: W10 F to W11 M
11.2.3 | Maker-Checker transcription into production |  | Business Analyst | Work package |  |  | 3
Z | Board demo preparation & rehearsal | 11.4.1 | Project Manager | Task | 2026-12-11 | 2026-12-16 | 4 | Y | 0 | YES | bar: W10 F to W11 W
11.4.1 | Demo preparation & rehearsal |  | Project Manager | Work package |  |  | 4
AA | ◆ Board demonstration | 11.4.2 | Project Manager | Milestone | 2026-12-16 | 2026-12-16 | 0 | Z, RP | 0 | YES | bar: W11 T
11.4.2 | Board demonstration — Week 11 |  | Project Manager | Work package |  |  | 1
| Client Demo Gate | Weeks 11–12 |  | Summary | 2026-12-17 | 2026-12-25 | 7 | bar: W11 T to W12 F
AB | Board feedback remediation | 11.5.1 | Shared — whole team | Task | 2026-12-17 | 2026-12-22 | 4 | AA | 0 | YES | bar: W11 T to W12 T
11.5.1 | Board feedback remediation |  | Shared — whole team | Work package |  |  | 5
AR | Buyer-review rehearsal & audit-trail pressure test | — | Shared — whole team | Task | 2026-12-23 | 2026-12-25 | 3 | AB | 0 | YES | bar: W12 W to W12 F
AC | ◆ Working client demo gate | 11.5.2 | Project Manager | Milestone | 2026-12-25 | 2026-12-25 | 0 | AR | 0 | YES | bar: W13 M
11.5.2 | Client demo gate — Week 12 |  | Project Manager | Work package |  |  | 1
| Buffer & Buyer Review | Weeks 13–14 |  | Summary | 2026-12-28 | 2027-01-08 | 10 | bar: W13 M to W14 F
AD | Project buffer — Weeks 13–14 | — | Shared — whole team | Buffer | 2026-12-28 | 2027-01-08 | 10 | AC | 0 | bar: W13 M to W14 F
AE | Contingent: evidence loading & hardening | 11.6.1 | Security Engineer ×2 | Task | 2026-12-28 | 2027-01-01 | 5 | AC | 5 | bar: W13 M to W13 F
11.6.1 | Contingent: evidence & hardening |  | Security Engineer ×2 | Work package |  |  | 5
AS | Contingent: deferred out-of-scope changes | 11.6.2 | Shared — whole team | Task | 2026-12-28 | 2026-12-31 | 4 | AC | 6 | bar: W13 M to W13 T
11.6.2 | Deferred out-of-scope change implementation |  | Shared — whole team | Work package |  |  | 4
AG | Closure report & lessons learned | 1.4.1 | Project Manager | Task | 2026-12-28 | 2026-12-31 | 4 | AC | 6 | bar: W13 M to W13 T
1.4.1 | Closure report & lessons learned |  | Project Manager | Work package |  |  | 4
AF | ◆ Major Buyer Review | 11.6.3 | Project Manager | Milestone | 2027-01-08 | 2027-01-08 | 0 | AD | 0 | bar: W14 F
11.6.3 | Major Buyer Review — Week 14 |  | Project Manager | Work package |  |  | 1

## Legend
How to read this chart
| Critical — zero float | Any slip here moves the Week 14 date. 28 of the 50 activities are critical.
| Has float | Slack before this activity affects the finish date. Float is in column J.
| Level of effort / hammock | Runs continuously alongside other work rather than as a discrete task.
| Project buffer | Weeks 13–14. Deliberate contingency ~15%, in front of the immovable Week 14 date.
| Milestone ◆ | Zero duration. It either happened or it did not.
| Summary / phase | Roll-up bar spanning its child activities.
Interval convention: ES/LS are start-points, EF/LF finish-points, EF = ES + duration. Day 1 of work is the interval 0→1.
Scope locks at the end of Week 3 (activity SL) after the hands-on hi-fi review. Every build activity depends on that milestone.
Testing runs inside each sprint (QP, QT2, QT3). Acceptance testing is by the QA Engineer and Business Analyst, not real users.
Mock/test data (RD) is built in Week 6 for E2E and UAT; the clean Maker-Checker load into production (RP) happens in Week 11.
Accepted changes outside the locked MVP scope are implemented in the Weeks 13–14 buffer (activity AS), not in the build.
Assumption: no public-holiday calendar is applied. Working days are Monday–Friday only.
Deferred — designed, not built this term, so not on the timeline: satellite monitoring (WBS 6.0, FR-05 — needs a commercial imagery subscription the team cannot procure) and the inter-registry flagging hook (WBS 9.4.1, FR-11 — no external registry to build against). The dashboard and data model reserve their place.