## WBS
Carbon Removal Verification Registry (CRVR) — Work Breakdown Structure
ITCS514 Software Project Management · Group 1 · Charter v2.00
Deliverable-based. 11 branches → 41 groups → 85 work packages → 301 person-days. Level 3 rows are the work packages: the unit that is estimated, owned and scheduled. Satellite monitoring (6.0) and the inter-registry hook (9.4) are deferred — designed, not built this term — and carry 0 pd (24 pd removed from the 325 pd full plan).
WBS | Work Package | Lvl | Owner | Effort (pd) | Acceptance Criteria | Charter ref | Activity
1.0 | Project Management | 1 |  | 40
1.1 | Initiation | 2 |  | 5
1.1.1 | Project charter & stakeholder register | 3 | Project Manager | 5 | Charter signed by Sponsor; 11 stakeholders registered with engagement approach |  | PM1
1.2 | Planning | 2 |  | 11
1.2.1 | WBS & schedule baseline | 3 | Project Manager | 4 | WBS passes 100% rule check; baseline Gantt with critical path identified |  | B
1.2.2 | Risk register | 3 | Project Manager | 3 | All risks scored, owned, with response strategy and trigger |  | BC
1.2.3 | Cost estimate & budget proposal | 3 | Project Manager | 4 | Board-ready budget covering all Charter §8.2 cost categories |  | BC
1.3 | Monitoring & Control | 2 |  | 8
1.3.1 | Weekly reporting & change control | 3 | Project Manager | 8 | Weekly status report issued Wk 0–14; change log maintained per §9.5 |  | PM1
1.4 | Closure | 2 |  | 4
1.4.1 | Closure report & lessons learned | 3 | Project Manager | 4 | Closure report accepted by Sponsor |  | AG
1.5 | Agile Ceremonies | 2 |  | 12
1.5.1 | Sprint planning & backlog refinement | 3 | Project Manager | 4 | Sprint goal and committed backlog recorded for every sprint |  | CER
1.5.2 | Daily stand-ups | 3 | Shared — whole team | 3 | Stand-up held each working day; blockers logged and owned |  | CER
1.5.3 | Sprint review & demo | 3 | Shared — whole team | 3 | Working software demonstrated to Sponsor at the end of every sprint |  | CER
1.5.4 | Sprint retrospective | 3 | Project Manager | 2 | Retrospective held per sprint with agreed actions carried forward |  | CER
2.0 | Requirements & Analysis | 1 |  | 23 |  | FR-01…FR-11
2.1 | Elicitation & Analysis | 2 |  | 7
2.1.1 | Stakeholder requirements workshops | 3 | Business Analyst | 4 | Workshops held with all 5 user-facing stakeholder groups; raw requirements logged |  | RQ
2.1.2 | As-is verification process & gap analysis | 3 | Business Analyst | 3 | As-is process documented; gaps mapped to Charter objectives 1–6 |  | RQ
2.2 | Requirements Specification | 2 |  | 8
2.2.1 | Functional requirements specification (FR-01…FR-11) | 3 | Business Analyst | 4 | Every charter functional requirement specified and testable |  | RS
2.2.2 | Non-functional, security & integration requirements | 3 | Business Analyst | 2 | NFR, security and integration requirements specified per Charter §4.2–4.4 |  | RS
2.2.3 | User stories & acceptance criteria | 3 | Business Analyst | 2 | Backlog written as stories with acceptance criteria, ready for Sprint 1 planning |  | RS
2.3 | Validation & Traceability | 2 |  | 3
2.3.1 | Requirements traceability matrix | 3 | Business Analyst | 2 | 100% of charter FRs and in-scope boundaries traced to a WBS package and a test case |  | RV
2.3.2 | Requirements baseline & sign-off | 3 | Business Analyst | 1 | Requirements baseline signed off by Sponsor before scope lock |  | RV
2.4 | Requirements Change Control | 2 |  | 5
2.4.1 | Change-request analysis & impact assessment | 3 | Business Analyst | 5 | Every post-lock change request analysed and dispositioned: in-sprint, deferred to buffer, or rejected |  | RC
3.0 | Design & Architecture | 1 |  | 36
3.1 | Feasibility Spikes | 2 |  | 10
3.1.1 | Satellite data provider spike | 3 | Infrastructure / DevOps | 5 | Provider selected; cost, revisit cadence and resolution documented; feasibility confirmed. Outcome: commercial imagery subscription not procurable this term → FR-05 build deferred (6.0) |  | C
3.1.2 | Geospatial / PostGIS spike | 3 | Full-stack Dev ×4 | 5 | Spatial intersection proven on sample boundaries; performance benchmarked |  | D
3.2 | System Architecture | 2 |  | 12
3.2.1 | Architecture & integration design | 3 | Infrastructure / DevOps | 5 | Architecture document approved at Week 3 design review |  | G
3.2.2 | Data model & access-control matrix | 3 | Full-stack Dev ×4 | 4 | 6 roles × permissions matrix signed off; ERD complete |  | G
3.2.3 | Ledger + WORM storage design | 3 | Security Engineer ×2 | 3 | Immutability approach documented and accepted (Assumption A-5) |  | H
3.3 | User Experience | 2 |  | 14
3.3.1 | Developer portal UX (responsive, phone width) | 3 | Designer ×2 | 5 | Hi-fi designs tested against low-capability developer personas |  | E
3.3.2 | Buyer & verifier portal UX | 3 | Designer ×2 | 5 | Hi-fi designs reviewed by Sponsor |  | F
3.3.3 | Hi-fi hands-on review — board member & champion customer | 3 | Designer ×2 | 2 | Sponsor, CEO, a board member and the champion customer have each used the hi-fi prototype; feedback logged and dispositioned |  | HF
3.3.4 | Design review & scope lock | 3 | Project Manager | 2 | Sponsor + CEO sign-off; scope formally locked at end of Week 3 before Week 4 build entry |  | I
4.0 | Project Registration | 1 |  | 21 |  | FR-01, FR-02
4.1 | Project Submission | 2 |  | 9
4.1.1 | Submission form & validation rules | 3 | Designer ×2 | 5 | Developer can submit a complete project; invalid data rejected with clear guidance |  | K
4.1.2 | Additionality reasoning capture | 3 | Full-stack Dev ×4 | 4 | Written reasoning + proof upload captured and stored (Charter FR-01) |  | K
4.2 | Evidence Management | 2 |  | 8
4.2.1 | Evidence upload service | 3 | Full-stack Dev ×4 | 4 | PDF, image, spreadsheet, GPS, land-title formats accepted |  | K
4.2.2 | WORM storage integration | 3 | Infrastructure / DevOps | 4 | Uploaded evidence written once; deletion/overwrite blocked and logged |  | K
4.3 | Project Lifecycle | 2 |  | 4
4.3.1 | Status tracking & dashboard | 3 | Designer ×2 | 4 | Developer and registry staff can see live project status; dashboard reserves the monitoring-alert slot (FR-05 deferred) |  | K
5.0 | Geospatial Boundary | 1 |  | 27 |  | FR-03, FR-04
5.1 | Boundary Registration | 2 |  | 13
5.1.1 | Data model & PostGIS setup | 3 | Full-stack Dev ×4 | 4 | Spatial schema deployed; CRS standardised |  | L
5.1.2 | Boundary registration service | 3 | Full-stack Dev ×4 | 5 | Boundary stored as validated geometry; area computed, not claimed |  | L
5.1.3 | GPS / geospatial file ingestion | 3 | Full-stack Dev ×4 | 4 | GeoJSON, KML and shapefile imports accepted and validated |  | L
5.2 | Map Interface | 2 |  | 5
5.2.1 | Responsive map-drawing interface (phone width) | 3 | Full-stack Dev ×4 | 5 | Non-technical user can draw a boundary on a phone (NFR usability) |  | L
5.3 | Overlap Detection | 2 |  | 9
5.3.1 | Overlap engine & tolerance rules | 3 | Full-stack Dev ×4 | 5 | Overlaps detected across all registered projects; GPS-error tolerance threshold applied |  | M
5.3.2 | Flagging & pre-issuance gate | 3 | Full-stack Dev ×4 | 4 | Flagged overlaps block credit issuance until investigated (Objective 4) |  | M
6.0 | Satellite Monitoring — DEFERRED | 1 |  | 0 | Designed in the solution and architecture, not built this term: it needs a commercial satellite imagery subscription the team cannot procure. The dashboard reserves a monitoring-alert slot and the data model stores monitoring records. Full-plan estimate 21 pd. | FR-05 (deferred)
6.1 | Satellite Integration | 2 |  | 0
6.1.1 | Provider API integration | 3 | Infrastructure / DevOps | 0 | DEFERRED — designed, not built this term. Original estimate 5 pd. When built: Imagery retrieved for a registered boundary |  | — (deferred)
6.1.2 | Imagery retrieval & clipping | 3 | Infrastructure / DevOps | 0 | DEFERRED — designed, not built this term. Original estimate 4 pd. When built: Imagery clipped to project polygon; per-project time series stored |  | — (deferred)
6.2 | Change Detection | 2 |  | 0
6.2.1 | Land-cover change & baseline | 3 | Full-stack Dev ×4 | 0 | DEFERRED — designed, not built this term. Original estimate 5 pd. When built: Baseline established; significant change detected on test data |  | — (deferred)
6.3 | Monitoring Output | 2 |  | 0
6.3.1 | Flags & alert generation | 3 | Full-stack Dev ×4 | 0 | DEFERRED — designed, not built this term. Original estimate 4 pd. When built: Change above threshold raises an investigation flag |  | — (deferred)
6.3.2 | Monitoring history view | 3 | Designer ×2 | 0 | DEFERRED — designed, not built this term. Original estimate 3 pd. When built: Monitoring timeline visible per project |  | — (deferred)
7.0 | Verification | 1 |  | 21 |  | Charter §5.3, FR-10
7.1 | Verifier Access | 2 |  | 8
7.1.1 | Assignment & evidence access | 3 | Full-stack Dev ×4 | 4 | Assigned verifier sees only their projects' evidence |  | O
7.1.2 | Verifier workspace UI | 3 | Designer ×2 | 4 | Verifier can review evidence in one place |  | O
7.2 | Verification Workflow | 2 |  | 9
7.2.1 | Verification report submission | 3 | Designer ×2 | 4 | Verifier submits structured verification report |  | O
7.2.2 | Registry review & approval | 3 | Full-stack Dev ×4 | 5 | Registry staff approve/reject with recorded rationale |  | O
7.3 | Verification Records | 2 |  | 4
7.3.1 | Traceable verification history | 3 | Full-stack Dev ×4 | 4 | Full verification chain retrievable per project |  | PZ
8.0 | Buyer Transparency | 1 |  | 21 |  | FR-08
8.1 | Buyer Portal | 2 |  | 8
8.1.1 | Buyer auth & project access | 3 | Full-stack Dev ×4 | 4 | Authorised buyer signs in and sees permitted projects only |  | Q
8.1.2 | Status & evidence view | 3 | Designer ×2 | 4 | Buyer sees verification status and permitted evidence |  | Q
8.2 | Traceability Views | 2 |  | 9
8.2.1 | Buyer-facing audit trail | 3 | Full-stack Dev ×4 | 5 | Buyer traces origin → evidence → verification → credit → audit (Week 14 requirement); monitoring step shows the reserved placeholder while FR-05 is deferred |  | Q
8.2.2 | Credit history & monitoring placeholder | 3 | Designer ×2 | 4 | Buyer sees credit history; monitoring panel shows the reserved placeholder (FR-05 deferred) |  | Q
8.3 | Privacy Controls | 2 |  | 4
8.3.1 | Privacy filtering & redaction | 3 | Security Engineer ×2 | 4 | Developer-sensitive fields never returned to buyer accounts |  | Q
9.0 | Security & Audit | 1 |  | 26 |  | FR-07, FR-09, FR-10, FR-11 (deferred)
9.1 | Access Control | 2 |  | 13
9.1.1 | Authentication (Keycloak/Auth0) | 3 | Security Engineer ×2 | 4 | All users authenticate; sessions managed securely |  | J
9.1.2 | Role-based access control | 3 | Security Engineer ×2 | 5 | Access matrix enforced; unauthorised access blocked and logged |  | J
9.1.3 | Separation of duties | 3 | Security Engineer ×2 | 4 | Same user cannot both submit and approve a critical action |  | P
9.2 | Audit Ledger | 2 |  | 9
9.2.1 | Cryptographic database ledger | 3 | Security Engineer ×2 | 5 | Ledger records hash-chained; tampering detectable |  | P
9.2.2 | Critical action recording | 3 | Full-stack Dev ×4 | 4 | 100% of critical verification and issuance actions recorded (Objective 5) |  | P
9.3 | Logging & Retention | 2 |  | 4
9.3.1 | Action logging & retention | 3 | Security Engineer ×2 | 4 | Admin actions logged; retention policy enforced |  | P
9.4 | Future Integration — DEFERRED | 2 |  | 0
9.4.1 | Inter-registry flagging hook | 3 | Full-stack Dev ×4 | 0 | DEFERRED — designed, not built this term. No external registry is connected, so there is no counterpart to build against; the endpoint and its data contract are designed so it can be added later without rework. Original estimate 3 pd. |  | — (deferred)
10.0 | Quality & Testing | 1 |  | 46
10.1 | Test Planning | 2 |  | 5
10.1.1 | Test plan, cases & test data | 3 | QA Engineer | 5 | Test cases traced to FR-01…FR-11 and to the user stories, before Sprint 2 build begins |  | QP
10.2 | In-Sprint Testing | 2 |  | 22
10.2.1 | Sprint 2 in-sprint module testing | 3 | QA Engineer | 5 | Every Sprint 2 module tested and defects raised before the Sprint 2 review |  | QT2
10.2.2 | Sprint 3 in-sprint module testing | 3 | QA Engineer | 5 | Every Sprint 3 module tested and defects raised before the Sprint 3 review |  | QT3
10.2.3 | End-to-end testing | 3 | QA Engineer | 5 | Full workflow validated: submission → verification → buyer view |  | U
10.2.4 | Security testing | 3 | Security Engineer ×2 | 4 | RBAC, separation of duties and audit integrity verified |  | V
10.2.5 | Usability testing | 3 | Designer ×2 | 3 | Submission completed unaided by a non-technical test user |  | U
10.3 | Acceptance Testing — QA & BA | 2 |  | 14
10.3.1 | Acceptance test scenarios from user stories | 3 | Business Analyst | 3 | Acceptance scenarios written for every user story in the sprint |  | QT2
10.3.2 | Sprint 2 acceptance testing (QA + BA) | 3 | QA Engineer | 4 | Sprint 2 increment accepted by QA and BA before the Sprint 2 review |  | QT2
10.3.3 | Sprint 3 acceptance testing (QA + BA) | 3 | QA Engineer | 4 | Sprint 3 increment accepted by QA and BA before the Sprint 3 review |  | QT3
10.3.4 | Acceptance sign-off & defect capture | 3 | Business Analyst | 3 | Each sprint increment signed off or rejected by the BA, with defects logged |  | QT3
10.4 | Defect Management | 2 |  | 5
10.4.1 | Triage & remediation verification | 3 | QA Engineer | 5 | All critical defects closed before Week 10 deployment |  | W
11.0 | Pilot & Deployment | 1 |  | 40
11.1 | Environments | 2 |  | 8
11.1.1 | Dev / test provisioning | 3 | Infrastructure / DevOps | 3 | Environments available to the team by end of Week 0 |  | A
11.1.2 | Production provisioning | 3 | Infrastructure / DevOps | 2 | Production environment running and deployable before Week 10 |  | X
11.1.3 | Security hardening | 3 | Security Engineer ×2 | 3 | Hardening checklist complete and signed off by Security Engineer |  | XS
11.2 | Pilot & Test Data | 2 |  | 7
11.2.1 | Pilot selection & evidence gathering | 3 | Project Manager | 2 | 1 pilot project agreed with Sponsor; real evidence obtained |  | RD
11.2.2 | Mock & test data set for E2E and UAT | 3 | Business Analyst | 2 | Test data set available in the test environment before E2E testing starts |  | RD
11.2.3 | Maker-Checker transcription into production | 3 | Business Analyst | 3 | Pilot data entered into production and independently checked, after E2E testing and deployment |  | RP
11.3 | Deployment | 2 |  | 4
11.3.1 | Production deployment | 3 | Infrastructure / DevOps | 4 | MVP live in production with rollback plan tested |  | Y
11.4 | Board Demonstration | 2 |  | 5
11.4.1 | Demo preparation & rehearsal | 3 | Project Manager | 4 | Demo script rehearsed end-to-end |  | Z
11.4.2 | Board demonstration — Week 11 ◆ | 3 | Project Manager | 1 | Week 11 milestone achieved; board feedback captured |  | AA
11.5 | Working Client Demo | 2 |  | 6
11.5.1 | Board feedback remediation | 3 | Shared — whole team | 5 | Prioritised board feedback implemented |  | AB
11.5.2 | Client demo gate — Week 12 ◆ | 3 | Project Manager | 1 | Week 12: a working client demo exists. This is the gate the buffer strategy depends on |  | AC
11.6 | Project Buffer · Weeks 13–14 | 2 |  | 10
11.6.1 | Contingent: evidence & hardening | 3 | Security Engineer ×2 | 5 | Buffer work. Done in Week 13 only if the buffer has not been consumed by upstream delay |  | AE
11.6.2 | Deferred out-of-scope change implementation | 3 | Shared — whole team | 4 | Accepted out-of-scope changes implemented in Weeks 13–14, or formally deferred to Phase 2 |  | AS
11.6.3 | Major Buyer Review — Week 14 ◆ | 3 | Project Manager | 1 | Week 14 milestone achieved; buyer traces origin → evidence → verification → credit → audit |  | AF
| TOTAL |  |  |  | Sum of level-3 work packages only — the 100% rule check.
Deferred items
6.0 Satellite Monitoring (FR-05, 21 pd) and 9.4.1 Inter-registry flagging hook (FR-11, 3 pd) are designed but not built this term. They stay in the WBS for traceability to the charter, carry 0 pd, and are not scheduled on the Gantt chart.

## Resource Loading
Resource loading — against the 65-day delivery window, Weeks 0–12
Role | People | Effort (pd) | Capacity (pd) | Load % | Flag
Project Manager | 1 | 46 | 65
Business Analyst | 1 | 35 | 65
Designers ×2 | 2 | 43 | 130
Full-stack Developers ×4 | 4 | 75 | 260
Security Engineers ×2 | 2 | 44 | 130
QA Engineer | 1 | 34 | 65
Infrastructure / DevOps | 1 | 24 | 65
Team total
Capacity = 65 working days (Weeks 0–12). Weeks 13–14 are project buffer and are deliberately not counted as capacity.
These are averages across the whole window. A week-by-week check drove the team sizing: Sprint 3 needed 4.7 developers in the full plan; deferring satellite monitoring removes 9 developer-days from it.
The Business Analyst is heavily loaded Weeks 0–3 for requirements, then drops to change-request analysis.
Every role fits every week after re-levelling; the residual peak is the PM in Week 3 at 105%.
Satellite monitoring (WBS 6.0, 21 pd) and the inter-registry hook (WBS 9.4.1, 3 pd) are deferred — designed, not built this term — and are excluded: Full-stack −12, Infrastructure/DevOps −9, Designers −3. Total 325 → 301 pd.